## CHECKLIST
Release Procedure Checklist
DONE | Build Procedure | NOTES
Finished | Increment version number TinyCLR if needed | MF\MicroFrameworkPK_v4_3\Solutions\EmoteDotNow\platform_selector.h
Finished | Increment version number TinyBooter if needed | DotNet-MF\MicroFrameworkPK_v4_3\Application\TinyBooter\TinyBooter.cpp
Finished | Increment version number of any dlls changed
| Update release change document |  | Finished
Finished | Generate release build binaries | Uncomment "COMPILE_CUSTOMER_RELEASE" define inplatform_selector.h. All files must be checked into git before building release build in order to build a 'clean' build. | N/A
Finished | Update Git release directory | DotNet-MF\MicroFrameworkPK_v4_3\Samraksh\Executables\Release; Create new release directory and copy in all binaries that were updated
Finished | Update Dropbox release directory | Dropbox (Samraksh)\Product - eMote\Releases\Release XX; Create new release directory and update binaries to the latest
Finished | Check in GitHub changes and tag as release build
DONE | Test Procedure | NOTES
Finished | Automated tests pass in Leesburg | Copy test receipts to Dropbox (Samraksh)\Product - eMote\Releases\<build directory
| Automated tests pass in Dublin | Copy test receipts to Dropbox (Samraksh)\Product - eMote\Releases\<build directory
N/A | Manual test - Neighbor count / liveness passes
Manual test - Overnight serial test passes
Manual test - Overnight radio test passes
Manual test - 2 channels ADC readings passes
Finished | Deployment of apps successful | Able to deploy all test apps in Dropbox (Samraksh)\Product - eMote\Releases\Release Procedure\Deployment tests
Finished | Deployment of new TinyCLR successful from TinyCLR | Make sure "Bootloader serial port" is correct; Might have to use menu option "Plugin->Debug->Reboot CLR"
Finished | Erase app is successful from MFDeploy - TinyBooter
Finished | Erase app is successful from MFDeploy - TinyCLR
Finished | Deployment of new TinyCLR successful from TinyBooter
Long range radio test successful
Finished | Save this checksheet in Dropbox release directory